## Milestone
Milestones
Milestone | Dependencies | Hours
Project repo readied | Project file structure | 4
| Basic class heirarchy | 2
Basic parser and lexer done | Basic and intermediate functions recognised | 6
Basic requirements | Int | 4
| Arithmetic | 12
| Declarations and local variables | 14
| Function arguments | 8
| Conditional structure | 10
Intermediate requirements | Stack functions (Context functions) | 16
| Loops | 10
| Enum | 6
| Switch | 9
| Arrays | 20
| Function calls | 10
| Break and continue | 5
Advanced lexer and parser | Advanced requirement syntax | 4
Advanced | Floats and doubles | 10
| Pointers | 20
| Sizeof | 8
| Advanced context | 10

## Schedule
Week | Date | Phase | Planned work
|  |  | Xin |  | Ebby
1 | 2021-02-23 | 1 | - Read documentations - Revise labs - Identify useful snippets in labs - Lay out basic parser and foundation | 4 | - Read documentations - Revise labs - Identify useful snippets in labs - Lay out basic parser and foundation | 4
2021-02-24
2021-02-25
2021-02-26
| 2021-02-27 | 2 | - Research: Stack structure - Implement: "int" type - Implement: Stack - Implement: Basic function | 14 | - Research: Arrays and loops - Implement: Advanced lexer and parser - Research: Arithmetic | 5
2 | 2021-02-28
2021-03-01
2021-03-02
2021-03-03
| 2021-03-04 | 3 | - Implement: Function argument - Implement: Arithmetic | 6 | - Research: Logical - Research: Primitives - Research: Assignment - Research: Context file structure | 8
2021-03-05
2021-03-06
3 | 2021-03-07 | 4 | - Implement: Declaration - Implement: Conditional - Implement: Arrays - Implement: Loops | 20 | - Research: Structure - Research: Globals - Research: Pointers - Research: Enums | 10
2021-03-08
2021-03-09
| 2021-03-10 | 5 | - Implement: Break and Continue - Implement: Sizeof - Implement: Switch | 10 | - Research: Floats and Doubles - Testing: Compiler tests | 5
2021-03-11
2021-03-12
4 | 2021-03-13 | 6 | - Refactoring | 5 | - Refactoring | 5
2021-03-14
2021-03-15
| 2021-03-16 | 7 | - Implement: Floats and doubles | 10 | - Research: Typedef and structures | 3
2021-03-17
2021-03-18
2021-03-19
5 | 2021-03-20 | 9 | - Implement: Pointers | 14
2021-03-21
2021-03-22
2021-03-23
| 2021-03-24 | 10 | - Clean and prepare for submission | 8 | - Clean and prepare for submission | 10

## Progress log
Week | Date | Phase | Actual work |  |  |  | Comments
|  |  | Xin |  | Ebby |  | Xin | Ebby
1 | 2021-02-23 | 1 | - Read documentations - Revise labs - Identify useful snippets in labs - Lay out basic parser and foundation | 8 | - Read documentations - Revise labs - Identify useful snippets in labs - Lay out basic parser and foundation | 6 | Had to spend more than expected time fully understanding the transition from parser to ast header files | Re-did some labs to revise and planned the project file directory
2021-02-24
2021-02-25
2021-02-26
| 2021-02-27 | 2 | - Research: Stack structure - Implement: "int" type - Implement: Stack - Implement: Basic function | 12 | - Research: Arrays and loops - Implement: Advanced lexer and parser - Research: Arithmetic | 10 | Slightly lower than planned effort but the stack would need to be more fortified as the project progresses. Most work spent in understanding directives and how frames are allocated and deallocated. | Underestimated the amount of things to research regarding arrays and how its implemented. Need to be careful to adjust the workload.
2 | 2021-02-28
2021-03-01
2021-03-02
2021-03-03
| 2021-03-04 | 3 | - Cleaning: Refactor code - Implement: Function argument - Implement: Arithmetic - Implement: Loops | 15 | - Research: Logical - Research: Primitives - Research: Assignment - Research: Context file structure | 8 | Meeting with Ebby agreed to shift more work onto me and he can spend more time on information processing. More time this week to fortify some code and beautify the codebase. | Spent more time on information processing so research time is limited to the planned hours.
2021-03-05
2021-03-06
3 | 2021-03-07 | 4 | - Implement: Declaration - Implement: Conditional - Implement: While | 20 | - Research: Structure - Research: Globals - Research: Pointers - Research: Enums | 18 | Research really helped to reduce time spent finding links but still overshot by alot | Probably would need to leave pointers and struct till last. A lot of things need to implemented and we might not have time.
2021-03-08
2021-03-09
| 2021-03-10 | 5 | - Implement: Break and Continue - Implement: Sizeof - Implement: Switch - Implement: Arrays | 24 | - Research: Floats and Doubles - Testing: Compiler tests | 4 | Final push to finish intermediate and clean up some loose ends
2021-03-11
2021-03-12
4 | 2021-03-13 | 6 | - Refactoring | 3 | - Refactoring | 3 | Cleaning up code base before progressing and reevaluating where we are and what we should do for compilers.
2021-03-14
2021-03-15
| 2021-03-16 | 7 | - Implement: Floats and doubles | 9 | - Research: Typedef and structures | 4 | Easier than expected with great information online and Ebby's links | Last topic to research and probably would not have time to do it. The scope of our project has been decided but just incase
2021-03-17
2021-03-18
2021-03-19
5 | 2021-03-20 | 9 | - Implement: Pointers - Implement: Function calls | 22 |  |  | Pointers is confusing and affects a lot of stuff in existing system. Function calls are implemented and works as intended. Spent way too much time on trying to get the pointers to work. Ended up leaving it as it is. | Leaving the implementation to Xin and covering information processing workload.
2021-03-21
2021-03-22
2021-03-23
| 2021-03-24 | 10 | - Clean and prepare for submission | 10 | - Clean and prepare for submission | 6 | Final clean up, spending the rest of the time on information processing