## Xin
Compiler Project Schedule
| Project Start Date | 2021-02-23 | [5 empty] | Display Week | 1 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
[10 empty] | 2021-02-22 | [6 empty] | 2021-03-01 | [6 empty] | 2021-03-08 | [6 empty] | 2021-03-15 | [6 empty] | 2021-03-22 | [6 empty] | 2021-03-29 | [6 empty] | 2021-04-05 | [6 empty] | 2021-04-12
 | time axis 2021-02-22 to 2021-04-18
Index | Task |  | PREDECESSOR | Start | End | Days | Predicted Hours | Hours | % | time axis 2021-02-22 to 2021-04-18
1 | Stage 1: Initiate project repo |  |  |  | -
1.1 | Revise labs |  |  | 2021-02-23 | 2021-02-23 | 1 | 1 | 3 | 100%
1.2 | Read documentations |  |  | 2021-02-23 | 2021-02-23 | 1 | 1 | 1 | 100%
1.3 | Plan compiler milestones |  |  | 2021-02-24 | 2021-02-24 | 1 | 1 | 1 | 100%
1.4 | Establish compiler class heirarchy |  |  | 2021-02-25 | 2021-02-25 | 1 | 1 | 3 | 100%
1.5 | Implement basic lexer and parser |  |  | 2021-02-26 | 2021-02-26 | 1 | 1 | 2 | 100%
1.6 | Set up project tracking |  |  | 2021-02-26 | 2021-02-26 | 1 | 1 | 2 | 100%
2 | Stage 2: Basic requirement |  |  |  | -
2.1 | Research the pointer and stack system |  |  | 2021-02-27 | 2021-02-27 | 1 | 5 | 4 | 100%
2.2 | Implement stack structure |  |  | 2021-02-28 | 2021-02-28 | 1 | 2 | 3 | 100%
2.3 | Implement INT data type |  |  | 2021-03-02 | 2021-03-02 | 1 | 3 | 2 | 100%
2.4 | Implement local variables |  |  | 2021-03-03 | 2021-03-03 | 1 | 2 | 3 | 100%
3 | Stage 3: Basic requirement |  |  |  | -
3.1 | Refactor code |  |  | 2021-03-04 | 2021-03-04 | 1 | 2 | 5 | 100%
3.2 | Implement arithmetic |  |  | 2021-03-04 | 2021-03-04 | 1 | 1 | 4 | 100%
3.3 | Implement function arguments |  |  | 2021-03-05 | 2021-03-05 | 1 | 2 | 4 | 100%
3.4 | Implement loops |  |  | 2021-03-06 | 2021-03-06 | 1 | 3 | 5 | 100%
4 | Stage 4: Intermediate requirement |  |  |  | -
4.1 | Implement variable declaration |  |  | 2021-03-06 | 2021-03-07 | 2 | 8 | 6 | 100%
4.2 | Implement conditional structure |  |  | 2021-03-08 | 2021-03-08 | 1 | 6 | 7 | 100%
4.3 | Implement while loop |  |  | 2021-03-08 | 2021-03-09 | 2 | 8 | 8 | 100%
5 | Stage 5: Advanced requirements |  |  |  | -
5.1 | Implement Break and Continue |  |  | 2021-03-09 | 2021-03-09 | 1 | 2 | 3 | 100%
5.2 | Implement Sizeof |  |  | 2021-03-10 | 2021-03-10 | 1 | 3 | 4 | 100%
5.3 | Implement Switch |  |  | 2021-03-11 | 2021-03-11 | 1 | 5 | 5 | 100%
5.4 | Implement Arrays |  |  | 2021-03-11 | 2021-03-13 | 3 | 15 | 12 | 100%
6 | Stage 6: Refactor |  |  |  | -
6.1 | Review class hierarchy |  |  | 2021-03-13 | 2021-03-13 | 1 | 3 | 2 | 100%
6.2 | Refactor code |  |  | 2021-03-14 | 2021-03-15 | 2 | 5 | 4 | 100%
7 | Stage 7: Advanced additional |  |  |  | -
7.1 | Implement float |  |  | 2021-03-16 | 2021-03-17 | 2 | 4 | 5 | 100%
7.2 | Implement double |  |  | 2021-03-18 | 2021-03-19 | 2 | 4 | 4 | 100%
8 | Stage 8: Advanced experimental |  |  |  | -
8.1 | Implement function calls |  |  | 2021-03-20 | 2021-03-21 | 2 | 12 | 10 | 100%
8.2 | Implement pointers |  |  | 2021-03-22 | 2021-03-23 | 2 | 12 | 12 | 70%
9 | Stage 9: Clean up |  |  |  | -
9.1 | Prepare submission |  |  | 2021-03-23 | 2021-03-24 | 2 | 12 | 10 | 100%
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on I7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on J7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).

## Ebby
Compiler Project Schedule
| Project Start Date | 2021-02-23 | [5 empty] | Display Week | 1 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
[10 empty] | 2021-02-22 | [6 empty] | 2021-03-01 | [6 empty] | 2021-03-08 | [6 empty] | 2021-03-15 | [6 empty] | 2021-03-22 | [6 empty] | 2021-03-29 | [6 empty] | 2021-04-05 | [6 empty] | 2021-04-12
 | time axis 2021-02-22 to 2021-04-18
Index | Task |  | PREDECESSOR | Start | End | Days | Predicted Hours | Hours | % | time axis 2021-02-22 to 2021-04-18
1 | Stage 1: Initiate project repo |  |  |  | -
1.1 | Revise labs |  |  | 2021-02-23 | 2021-02-23 | 1 | 1 | 2 | 100%
1.2 | Read documentations |  |  | 2021-02-23 | 2021-02-23 | 1 | 2 | 2 | 100%
1.3 | Plan compiler milestones |  |  | 2021-02-24 | 2021-02-24 | 1 | 2 | 2 | 100%
2 | Stage 2: Basic requirement |  |  |  | -
2.1 | Research array and loops |  |  | 2021-02-27 | 2021-02-27 | 1 | 1 | 6 | 80%
2.2 | Implement advanced lexer and parser |  |  | 2021-02-28 | 2021-02-28 | 1 | 3 | 2 | 100%
2.3 | Research arithmetic |  |  | 2/29/2021 | 2021-03-01 | 1 | 2 | 3 | 100%
3 | Stage 3: Basic requirement |  |  |  | -
3.1 | Research logical structure |  |  | 2021-03-02 | 2021-03-02 | 1 | 4 | 3 | 100%
3.2 | Research primitives |  |  | 2021-03-03 | 2021-03-03 | 1 | 1 | 2 | 100%
3.3 | Research assignments |  |  | 2021-03-03 | 2021-03-03 | 1 | 1 | 3 | 100%
3.4 | Implement lexer hack, work on early class heirarchy for advanced features |  |  | 2021-03-04 | 2021-03-04 | 1 | 9 | 7 | 100%
4 | Stage 4: Intermediate requirement |  |  |  | -
4.1 | Research structures |  |  | 2021-03-05 | 2021-03-05 | 1 | 4 | 3 | 100%
4.2 | Research globals |  |  | 2021-03-06 | 2021-03-06 | 1 | 2 | 2 | 100%
4.3 | Research enums |  |  | 2021-03-06 | 2021-03-06 | 1 | 4 | 2 | 60%
4.4 | Research pointers |  |  | 2021-03-07 | 2021-03-07 | 1 | 2 | 1 | 100%
5 | Stage 5: Advanced requirements |  |  |  | -
5.1 | Research floats and doubles |  |  | 2021-03-08 | 2021-03-08 | 1 | 1 | 4 | 100%
5.2 | Use compiler tests |  |  | 2021-03-09 | 2021-03-09 | 1 | 12 | 6 | 100%
6 | Stage 6: Refactor |  |  |  | -
6.1 | Code refactor |  |  | 2021-03-13 | 2021-03-13 | 1 | 6 | 2 | 100%
7 | Stage 7: Advanced additional |  |  |  | -
7.1 | Research function calls |  |  | 2021-03-14 | 2021-03-15 | 2 | 2 | 3 | 100%
7.2 | Research type def |  |  | 2021-03-16 | 2021-03-16 | 1 | 1 | 1 | 80%
7.3 | Implement pointers |  |  | 2021-03-18 | 2021-03-20 | 3 | 9 | 1 | 20%
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on I7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on J7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).